## Sheet1
Project Communications Schedule
Communication | Frequency | Goal | Owner
Discord
Pre-Sprint | start of milestone | Review product backlog Log issues from requirements elicitation review team member roles Progress Plan | Project manager Team members
Task Status Report | Daily | Report task progress Report issues found Report issues fixed Report plan to complete task | Project manager Team members
Project status Report | Weekly | Report progress for sprint role Report issues found Report issues fixed Report plan to complete deliverable for sprint | Project manager
Post-sprint | end of milestone | Deliverables Achieved Deliverables Failed Changes needed Progess Plan
GitHub
TODO: | Daily | Check for issues | Project manager Team members
Backlog | Daily as needed | Record issues found Record Issues Fixed | Project manager Team members
Test Screenshots | Upon test | Document test completion | Project manager
Zoom
Milestone Status Report | end of milestone | Milestone progress Barriers encountered Elicit Progress Plan | Project Manager Client